**Ventura County CoC Coordinated Entry System**

The Coordinated Entry and Assessment System is a HUD requirement to coordinate the process for intake, assessment and provision of referrals and to create a system for prioritization of resources based on level of need.

|  |  |  |
| --- | --- | --- |
| **Phase** | **Objectives** | **Target completion** |
| **Pilot**  | * Ventura H2H Pilot
 | Complete |
| **Development of prioritization standards** | * Countywide Coordinated Entry workgroup began meeting Jan 2015-March 2015
* Develop drafted policies and procedures for prioritization and matching
 | VI-SPDAT training March 26, 2015First round of matching for housing mid April 2015Second round of training TBD |
| **Data Sharing** | * Develop MOU for HMIS data sharing; ROI and Client consent for data sharing
* Approved by County Counsel
 | MOUs to be signed by all participating agencies by end of April 2015HMIS system open for data sharing once all MOUs are in place |
| **Services Inventory** | * CoC Inventory: All CoC vacancies will be filled through the Coordinated Entry System
 | 41 CoC units dedicated to chronically homeless |
| **Coordination of Services and System Entry** | * Development of workgroup. Focus on Access, Referral, Client flow through System
* Connecting clients with the most appropriate services quickly
 | Meeting TBA |